## Dashboard
AXUDAR GROUP™ – WEBSITE QA PROGRESS DASHBOARD
Build: https://auxder.vercel.app/ • Source: QA & Developer Action List, 03 October 2026
Total Items | Dev Complete % | QA Passed % | Client Approved % | Fully Closed %
29 | 0% | 0% | 0% | 0%
READY TO RETURN FOR QA? | NO – 21 critical/high item(s) still open
By Priority – Developer Status
Priority | Total | Open | In Progress | Done – Ready for QA | Blocked | % Dev Done
CRITICAL | 5 | 5 | 0 | 0 | 0 | 0%
HIGH | 16 | 16 | 0 | 0 | 0 | 0%
MEDIUM | 8 | 8 | 0 | 0 | 0 | 0%
TOTAL | 29 | 29 | 0 | 0 | 0 | 0%
Overall Status Breakdown |  |  |  | QA & Client Snapshot
Status | Items | % of Total |  | Measure |  | Items
OPEN | 29 | 100% |  | QA Not Tested |  | 29
IN PROGRESS | 0 | 0% |  | QA Pass |  | 0
AWAITING QA | 0 | 0% |  | QA Fail – Reopen |  | 0
REOPENED | 0 | 0% |  | QA Retest Needed |  | 0
AWAITING CLIENT | 0 | 0% |  | Client Pending |  | 29
BLOCKED | 0 | 0% |  | Client Approved |  | 0
CLOSED | 0 | 0% |  | Client Changes Req. |  | 0
TOTAL | 29 | 100%
Regression (passed items) still passing: |  |  | 0 / 6
Return-for-QA checklist complete: |  |  | 0%

## Action Tracker
AXUDAR GROUP™ – Website QA Action Tracker (build: https://auxder.vercel.app/ • list dated 03 Oct 2026)
Edit the shaded input columns (G–I, J–L, M–O, P–Q). Column R is automatic.
ID | Priority | Area | Issue | Current Problem | Required Fix | Tested Desktop? | Tested Mobile? | Developer | Dev Status | Dev Date Completed | Dev Notes / Test Evidence (URL/screenshot) | QA Status | QA Date | QA Feedback | Client Review | Client Comments | Overall Status
C1 | CRITICAL | Enquiry flow | SEO enquiry carries the wrong package | Selecting SEO & AI Visibility at FROM £649 + VAT opens an enquiry showing Social Media Growth £399. | SEO must carry SEO & AI Visibility and £649 through every enquiry step. Test homepage → package → enquiry and SEO detail page → enquiry. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
C2 | CRITICAL | Navigation / CTA | Main “BUILD YOUR GROWTH CANVAS” CTA is wrong | The header CTA routes to Contact instead of starting/opening the Growth Canvas. | Route this CTA directly to the Growth Canvas journey. It must not behave like Contact. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
C3 | CRITICAL | Content | Service pages contain copied Business Growth content | Strategy, Marketing, SEO, Social Media and Website & Conversion are still using Business Growth copy/deliverables. | Replace each page with its own approved service-specific hero copy, outcomes, deliverables and CTAs. No duplicated Business Growth content. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
C4 | CRITICAL | Site architecture | Core journeys are not separate as requested | Ecosystem, Growth Canvas and How It Works still resolve into / depend on homepage sections instead of clear standalone journeys. | Create the agreed distinct routes/pages and ensure top navigation opens the correct page/route for each. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
C5 | CRITICAL | Enquiry flow | Canvas → enquiry handoff is not fully reliable/clear | The Canvas can hold selections, but the journey into enquiry is not clearly carrying and displaying all chosen areas/outcomes. | When “Discuss My Canvas” is used, show the selected Canvas areas/outcomes clearly on the enquiry screen and include them in the submitted enquiry. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H1 | HIGH | Contact form | Contact form categories do not match the six Growth Areas | Contact uses Strategy & Planning / Commercial Growth / SEO & AI Visibility / Social & Content / Website & Conversion / Campaigns & Leads. | Use exactly: Business Growth; Strategy; Marketing; SEO & AI Visibility; Social Media; Website & Conversion. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H2 | HIGH | Terminology | “Strategy & Planning” still appears | Legacy wording remains across pages, Canvas and footer. | Replace all customer-facing “Strategy & Planning” references with “Strategy”. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H3 | HIGH | Terminology | “Connected Growth Solutions” wording is wrong | Homepage still uses “6 Connected Growth Solutions”. | Change to “6 Connected Growth Areas”. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H4 | HIGH | Terminology | Growth Engine wording remains | Legacy “Growth Engine” wording is still visible. | Remove legacy Growth Engine wording and use the new Growth Ecosystem / Growth Canvas terminology only. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H5 | HIGH | Terminology | 12-month wording remains | “12 Month Partnership Model” and 12-month minimum wording are still visible. | Remove the legacy 12-month partnership/minimum wording where previously requested. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H6 | HIGH | Content | SEO package detail page is incomplete/wrong | The SEO detail page contains Business Growth/sales/pricing copy instead of full SEO content. | Build the SEO page with the approved SEO & AI Visibility package content, deliverables and FROM £649 + VAT pricing. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H7 | HIGH | Enquiry flow | “Ask a question” loses package context | A package can be passed in the URL but the visible form does not clearly show the customer what package they are asking about. | Display the selected package name clearly on the form and include it in the submitted enquiry. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H8 | HIGH | Contact form | Enquiry CTA wording is still old | Contact still uses “PREPARE MY ENQUIRY”. | Use “SEND MY ENQUIRY” and, for Canvas-led enquiries, “SEND MY GROWTH CANVAS”. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H9 | HIGH | Contact form | Submission confirmation must be clear | The final success state is not aligned to the requested messaging. | After successful submission show a clear confirmation headed “WE’VE GOT YOUR ENQUIRY”. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H10 | HIGH | Navigation / CTA | Canvas pages are too isolated | /area/ pages do not present the normal site navigation/header clearly enough. | Maintain standard site navigation/back route so users never feel trapped in the Canvas journey. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H11 | HIGH | Navigation / CTA | Service-to-service navigation is missing | The requested Previous / All / Next navigation is not clearly present on service pages. | Add Previous / All Services / Next navigation consistently to all six service pages. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H12 | HIGH | Terminology | Process terminology/numbering inconsistent | Process still starts with Strategy & Planning and numbering changes from 1,2,3 to 04. | Use current terminology and one numbering format throughout. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H13 | HIGH | Content | Duplicate testimonial content remains | James Whitfield / Meridian Capital Group is repeated multiple times. | Remove duplicate/placeholder testimonials. Use only approved real testimonial content. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H14 | HIGH | Content | Unrelated fundraiser FAQ remains | “How long does a fundraiser run?” is still visible. | Remove the unrelated fundraiser FAQ completely. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H15 | HIGH | Footer / Legal | Old US address remains | 10808 Foothill Blvd, Rancho Cucamonga, CA is still visible in the footer/site. | Remove the US address and replace with the approved Axudar contact details only. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
H16 | HIGH | Footer / Legal | Footer structure is wrong | Contact details sit under a “LEADERSHIP” heading and old taxonomy remains. | Rebuild footer labels so Contact details, navigation and six Growth Areas are correctly named and grouped. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M1 | MEDIUM | Content | Results page structure differs from agreed format | Page uses Problem → Growth Canvas Plan → What Axudar Did → Result. | Use Challenge → Canvas → Delivery → Result, unless explicitly re-approved. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M2 | MEDIUM | Content | Results messaging conflicts with disclaimer | “Real businesses. Real outcomes.” appears alongside wording that names/data may be indicative. | Make claims/disclaimer consistent and unambiguous. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M3 | MEDIUM | SEO / Meta | Insight page titles are generic | Individual Insights are using the generic Axudar page title. | Give every Insight article its own SEO title and description. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M4 | MEDIUM | SEO / Meta | Service page SEO titles contain duplication | Examples contain “Axudar Group ¦ Axudar Group”. | Use a single, unique page title per service. Remove duplicate brand text. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M5 | MEDIUM | SEO / Meta | Contact page SEO title is generic | Contact uses the generic site title. | Use a unique Contact page title/meta description. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M6 | MEDIUM | Footer / Legal | Legal/privacy destinations are not surfaced | Privacy, Cookies and Terms are not clearly surfaced in the footer/contact flow. | Add Privacy Policy, Cookie Policy and Terms links and a privacy acknowledgement around data submission as appropriate. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M7 | MEDIUM | Content | SEO Dictionary cannot be found | The previously requested SEO Dictionary/unique topic structure is not visible in the current public journey. | Add/restore the approved SEO Dictionary content and ensure it is reachable from the intended location. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN
M8 | MEDIUM | Site architecture | Legacy route naming remains | Package URLs still expose /readyMadePackageDetails/. | Rename/redirect legacy “Ready Made” routes where feasible so the public architecture matches the new proposition. | No | No |  | Open |  |  | Not Tested |  |  | Pending |  | OPEN

## Regression (Passed)
Passed / Improved Items – re-verify after fixes (do not regress)
ID | Item | Status in 03 Oct QA | Regression Result | Checked By | Date Checked | Notes
P1 | Six “Choose Where You Need Support” cards link to service areas | PASS / IMPROVED | Not Rechecked
P2 | Six “+ Add to My Growth Canvas” links now pre-load Canvas areas | PASS / IMPROVED | Not Rechecked
P3 | Headline Social Media price shows FROM £399 + VAT | PASS | Not Rechecked
P4 | Headline SEO & AI Visibility price shows FROM £649 + VAT | PASS | Not Rechecked
P5 | Insights landing page and checked articles open | PASS | Not Rechecked
P6 | Main phone number displays as 0330 133 5720 | PASS | Not Rechecked

## Return-for-QA Checklist
Return-for-QA Checklist – complete every line before re-submitting
# | Checklist Item | Status | Completed By | Date | Notes
1 | All C1–C5 critical items completed and tested. | Not Started
2 | All H1–H16 high-priority items completed. | Not Started
3 | Every top-navigation link checked on desktop and mobile. | Not Started
4 | Every clickable service card/box checked on desktop and mobile. | Not Started
5 | Every “Add to My Growth Canvas” action checked. | Not Started
6 | Every package CTA checked through to the final enquiry screen. | Not Started
7 | All form fields, validation, submit action and confirmation state tested. | Not Started
8 | Correct package/service name and price retained throughout the journey. | Not Started
9 | No old terminology remains: Strategy & Planning / Growth Engine / Ready Made / 12 Month Partnership Model. | Not Started
10 | No placeholder, duplicated or unrelated content remains. | Not Started
11 | Footer, contact details and legal links checked on every template. | Not Started
12 | Page titles/meta checked for homepage, six services, packages, Results, Insights articles and Contact. | Not Started
13 | Final mobile check completed at common phone widths before resubmission. | Not Started
| Checklist completion | 0%

## Legend & Lists
Developer Status | QA Status | Client Review | Checklist Status | Regression Result | Priority
Open | Not Tested | Pending | Not Started | Not Rechecked | CRITICAL
In Progress | Pass | Approved | In Progress | Still Passing | HIGH
Done – Ready for QA | Fail – Reopen | Changes Requested | Complete | Regressed | MEDIUM
Blocked / Cannot Complete | Retest Needed |  | N/A
How to use
• Developer sets Dev Status (and Date Completed) after testing on desktop AND mobile.
• QA sets QA Status after independent retest. Fail – Reopen puts the item back to work.
• Client sets Client Review once QA has passed. Yellow-bordered columns are the ones to edit.
• An item is fully CLOSED only when Dev = Done, QA = Pass and Client = Approved.
• Dashboard and Checklist totals recalculate automatically from the tracker.